## Slide 1
1. Cumulative Board

## Slide 2
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Prediction of Knee Osteporosis by DL
Legend
Max
Shas
Sergey
Define project scope and goals
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Research relevant literature
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Research existing solutions
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Organize dataset and data loading
Start date: 02/07
Expected Review date: 01/07
Reviewer: All
Set up project repository and collaboration tools
Start date: 02/07
Expected Review date: 07/07
Reviewer: All
Images preprocessing literature review
Start date: 02/07
Expected Review date: 07/07
Reviewer: All
Apply data augmentation techniques
Start date: 06/07
Expected Review date: 14/07
Reviewer: All
Preprocessing (images resizing, normalization, etc.)
Start date: 06/07
Expected Review date: 14/07
Reviewer: All
Verify preprocessing steps
Start date: 06/07
Expected Review date: 14/07
Reviewer: All
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All

## Slide 3
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Prediction of Knee Osteporosis by DL
Legend
Max
Shas
Sergey
Load and configure a pretrained model (VGG-16, etc.)
Start date: 22/07
Expected Review date: 28/07
Reviewer: All
Fine-tune the pretrained model on the knew x-ray dataset
Start date: 22/07
Expected Review date: 28/07
Reviewer: All
Compare results of the improved models against the baseline
Start date: 22/07
Expected Review date: 28/07
Reviewer: All

## Slide 4
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Prediction of Knee Osteporosis by DL
Legend
Max
Shas
Sergey
Set up hyper-paramer tuning (grid search, random search)
Start date: 29/07
Expected Review date: 04/08
Reviewer: All
Optimize training process (learning rate, batch size)
Start date: 29/07
Expected Review date: 04/08
Reviewer: All
Conduct hyper-parameter tuning experiments
Start date: 29/07
Expected Review date: 04/08
Reviewer: All

## Slide 5
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Prediction of Knee Osteporosis by DL
Legend
Max
Shas
Sergey
Evaluate final model on validation and test sets
Start date: 06/08
Expected Review date: 11/08
Reviewer: All
Implement model performance metrics
Start date: 06/08
Expected Review date: 11/08
Reviewer: All
Prepare project report and presentation
Start date: 06/08
Expected Review date: 11/08
Reviewer: All

## Slide 6
2. Weekly Board

## Slide 7
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Prediction of Knee Osteporosis by DL
Legend
Max
Shas
Sergey
Define project scope and goals
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Research relevant literature
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Research existing solutions
Start date: 25/06
Expected Review date: 01/07
Reviewer: All
Week 1: Project Selection and Initial Literature Survey

## Slide 8
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 2: Project Setup and Project Management
Organize dataset and data loading
Start date: 02/07
Expected Review date: 01/07
Reviewer: All
Set up project repository and collaboration tools
Start date: 02/07
Expected Review date: 07/07
Reviewer: All
Images preprocessing literature review
Start date: 02/07
Expected Review date: 07/07
Reviewer: All

## Slide 9
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 3: Data Preprocessing and EDA
Apply data augmentation techniques
Start date: 06/07
Expected Review date: 14/07
Reviewer: All
Preprocessing (images resizing, normalization, etc.)
Start date: 06/07
Expected Review date: 14/07
Reviewer: All
Verify preprocessing steps
Start date: 06/07
Expected Review date: 14/07
Reviewer: All

## Slide 10
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 4: Model Selection and Design
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All
Design architecture of a CNN model and implement a baseline model
Start date: 16/07
Expected Review date: 21/07
Reviewer: All

## Slide 11
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 5: Model Improvement and Transfer Learning
Load and configure a pretrained model (VGG-16, etc.)
Start date: 22/07
Expected Review date: 28/07
Reviewer: All
Fine-tune the pretrained model on the knew x-ray dataset
Start date: 22/07
Expected Review date: 28/07
Reviewer: All
Compare results of the improved models against the baseline
Start date: 22/07
Expected Review date: 28/07
Reviewer: All

## Slide 12
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 6: Model Analysis and Optimization
Set up hyper-paramer tuning (grid search, random search)
Start date: 29/07
Expected Review date: 04/08
Reviewer: All
Optimize training process (learning rate, batch size)
Start date: 29/07
Expected Review date: 04/08
Reviewer: All
Conduct hyper-parameter tuning experiments
Start date: 29/07
Expected Review date: 04/08
Reviewer: All

## Slide 13
Backlog
To Do
In Progress
In Review
Done
Team 8 Capstone: Knee Osteporosis Classification
Legend
Max
Shas
Sergey
Week 7: Model Evaluation and Deployment
Evaluate final model on validation and test sets
Start date: 06/08
Expected Review date: 11/08
Reviewer: All
Implement model performance metrics
Start date: 06/08
Expected Review date: 11/08
Reviewer: All
Prepare project report and presentation
Start date: 06/08
Expected Review date: 11/08
Reviewer: All